## 項目
階段類型 | 功能分類 | 模塊子列 | 研究狀態 | 預計開始日期 | 預計完成天數 | 預計結束時間 | 實際結束時間 | 備註
開發初期階段 | 概念企劃 | 概念企劃文件 | 已完成 | - | - | - | -
| 論述文件 | 企劃文件
|  | 角色設計文件 | 90%
|  | 物品設計文件 | 80%
| 過程設計 | 遊戲模式 | 已完成
遊戲規則
遊戲時間系統
遊戲進程
| 世界觀設定 | 遊戲故事設計模式
故事情節與故事事件
遊戲劇本與任務系統
| 機制設計 | 傷害機制 | 已完成
|  | 護盾機制 | 已完成
|  | 附魔 | 已完成
|  | 精鍊 | 已完成
|  | 合成 | 已完成
|  | 鑲環 | 已完成
|  | 小型秘物序列 | 已完成
|  | 大型秘物序列 | 已完成
|  | 技能機制 | 已完成
|  | 效果機制 | 已完成
|  | 天賦 | 已完成
開發中期階段 | 角色設計 | 法師(維茲傑雷)
秘術師(贊尼亞蘇)
巫師(恩尼德)
術士(奈法蘭)
| 場景與關卡設計 | 第一大關設計草稿 | 已完成
|  | 第一大關抽象場景設計 | 已完成
第一大關具體場景設計
第一大關場景打磨
第二大關設計草稿
第二大關抽象場景設計
第二大關具體場景設計
第二大關場景打磨
第三大關設計草稿
第三大關抽象場景設計
第三大關具體場景設計
第三大關場景打磨
第四大關設計草稿
第四大關抽象場景設計
第四大關具體場景設計
第四大關場景打磨
第五大關設計草稿
第五大關抽象場景設計
第五大關具體場景設計
第五大關場景打磨
第六大關設計草稿
第六大關抽象場景設計
第六大關具體場景設計
第六大關場景打磨
開發後期階段 | 介面設計 | 根據魔獸提供的工具設計介面
| 美術設計 | 遊戲美術風格
角色造型設計
遊戲環境設計
掌控整體視覺設計
| 互動設計 | 遊戲畫面設計
音樂音效

## 重構紀錄
data | buffs | init |  |  | 2018-12-17 |  | 2019-05-04
|  | 冰凍 |  |  | v
|  | 定身 |  |  | v
|  | 暈眩 |  |  | v
|  | 束縛 |  |  | v
|  | 沉默 |  |  | v
|  | 減攻速 |  |  | v
|  | 減速 |  |  | v
|  | 繳械 |  |  | v
| heros | 冰霜秘術師 | skills | 召喚水元素 | v
|  |  |  | 寒冰箭 | v
|  |  |  | 暴風雪 | v
|  |  |  | 霜之環 | v
|  |  |  | 霜寒刺骨 | v
|  |  | talents | 冬之蕭瑟 | v
|  |  |  | 冰晶 | v
|  |  |  | 冰晶裂片 | v
|  |  |  | 冰雪襲境 | v
|  |  |  | 冰霜長矛 | v
|  |  |  | 嚴寒壓境 | v
|  |  |  | 霜雪暴 | v
|  | hero_list |  |  | v
|  | init |  |  | v
| quests | init |  |  | v
|  | 報到 |  |  | v
|  | 入營試煉 |  |  | v
|  | 學習附魔 |  |  | v
|  | 選擇天賦 |  |  | v
|  | 精煉裝備 |  |  | v
|  | 第一次試煉 |  |  | v
| monsters | general_node | period |  | v
|  |  | wait |  | v
|  | 物品測試員 | behavior |  | v
|  |  | skill |  | v
|  | 豺狼守望者 | behavior |  | v
|  |  | skill |  | v
| attributes |  |  |  | v
| combinations |  |  |  | v
| drop_lib |  |  |  | v
| equipment_template |  |  |  | v
| info_in_position |  |  |  | v
| intensify_attribute |  |  |  | v
| prefix_lib |  |  |  | v
| recipe_lib |  |  |  | v
| regions |  |  |  | v
| secrets_lib |  |  |  | v
lib | bar | castbar |  |  | v | v
|  | core |  |  | v | v
|  | shield |  |  | v | v
| buff | attribute | init |  | v | v
|  |  | 剩餘時間 |  | v | v
|  | core |  |  | v | v
|  | init |  |  | v | v
|  | operator |  |  | v | v
|  | unit |  |  | v | v
| combat | checker |  |  | v | v
|  | conversion |  |  | v | v
|  | damage |  |  | v | v
|  | heal |  |  | v | v
|  | num |  |  | v | v
|  | type |  |  | v | v
| group | condition |  |  | v | v
|  | core |  |  | v | v
| item | equipment | core |  | v
|  |  | printer |  | v
|  | add_recipe |  |  | v
|  | big_secret_order |  |  | v
|  | combine |  |  | v
|  | core |  |  | v
|  | enchanted |  |  | v
|  | event |  |  | v
|  | exten_hole |  |  | v
|  | init |  |  | v
|  | intensify |  |  | v
|  | prefix |  |  | v
|  | produce_recipe |  |  | v
|  | secrets |  |  | v
|  | small_secret_order |  |  | v
| mover | core |  |  | v | v
|  | knock |  |  | v | v
|  | missile |  |  | v | v
|  | trace |  |  | v | v
|  | util |  |  | v | v
| quest | core |  |  | v | v
|  | unit |  |  | v | v
|  | util |  |  | v
| skill | cast |  |  | v | v
|  | core |  |  | v | v
|  | event |  |  | v | v
|  | init |  |  | v | v
|  | util |  |  | v | v
| texttag | arc |  |  | v | v
|  | core |  |  | v | v
| timer | core |  |  | v | v
|  | init |  |  | v | v
| unit | attribute | init |  | v | v
|  |  | 攻擊速度 |  | v | v
|  |  | 攻擊間隔 |  | v | v
|  |  | 施法速度 |  | v | v
|  |  | 最大物理攻擊力 |  | v | v
|  |  | 最小物理攻擊力 |  | v | v
|  |  | 物理攻擊力 |  | v | v
|  |  | 物理護甲 |  | v | v
|  |  | 生命 |  | v | v
|  |  | 生命上限 |  | v | v
|  |  | 移動速度 |  | v | v
|  |  | 轉身速度 |  | v | v
|  |  | 魔力 |  | v | v
|  |  | 魔力上限 |  | v | v
|  | core |  |  | v | v
|  | event |  |  | v | v
|  | hero |  |  | v | v
|  | operator |  |  | v | v
|  | pet |  |  | v | v
| dialog |  |  |  | v | v
| event |  |  |  | v | v
| game |  |  |  | v | v
| intelligence |  |  |  | v | v
| leaderboard |  |  |  | v | v
| map |  |  |  | v | v
| nultiboard |  |  |  | v | v
| player |  |  |  | v | v
| point |  |  |  | v | v
| polygon |  |  |  | v | v
| region |  |  |  | v | v
| talent |  |  |  | v | v
| trigger |  |  |  | v | v
test | add_recipe |  |  |  | v
| arc_texttag |  |  |  | v | v
| array |  |  |  | v | v
| bar |  |  |  | v | v
| behavior_tree1 |  |  |  | v | v
| behavior_tree2 |  |  |  | v | v
| big_secret_order |  |  |  | v
| buff |  |  |  | v
| build_table |  |  |  | v | v
| call_func_in_table |  |  |  | v | v
| castbar |  |  |  | v | v
| class |  |  |  | v | v
| color |  |  |  | v | v
| combine |  |  |  | v
| core |  |  |  | v
| create_pathindicator |  |  |  | v
| damage |  |  |  | v
| dialog |  |  |  | v | v
| enchanted |  |  |  | v
| equipment |  |  |  | v
| event |  |  |  | v | v
| extend_hole |  |  |  | v
| game |  |  |  | v | v
| greatest_common_factor |  |  |  | v | v
| group |  |  |  | v | v
| hero |  |  |  | v | v
| hexadecimal |  |  |  | v | v
| intelligence |  |  |  | v | v
| intensify_attribute |  |  |  | v
| item |  |  |  | v
| knock |  |  |  | v | v
| list |  |  |  | v | v
| math_lib |  |  |  | v | v
| memoizing |  |  |  | v
| missile |  |  |  | v | v
| mover |  |  |  |  | v
| node |  |  |  | v | v
| pairs_by_key |  |  |  | v | v
| pet |  |  |  | v | v
| player |  |  |  | v | v
| point |  |  |  | v | v
| polygon |  |  |  | v | v
| prefix_lib |  |  |  | v
| produce_recipe |  |  |  | v
| quest_progress |  |  |  | v
| quest |  |  |  | v
| queue |  |  |  | v | v
| random_number_generator |  |  |  | v | v
| regex |  |  |  | v | v
| region |  |  |  | v | v
| secrets_lib |  |  |  | v
| shield |  |  |  | v | v
| skill |  |  |  | v
| small_secret_oreder |  |  |  | v
| stack |  |  |  | v | v
| table_call_by_what |  |  |  | v | v
| talent |  |  |  | v
| texttag |  |  |  | v | v
| timer |  |  |  | v | v
| trigger |  |  |  | v | v
| try_catch |  |  |  | v | v
| unit_event |  |  |  | v | v
| unit |  |  |  | v | v
util | behavior_tree | node_types | active_priority |  | v
|  |  | always_fail_decorator |  | v
|  |  | always_suecceed_decorator |  | v
|  |  | branch_node |  | v
|  |  | decorator |  | v
|  |  | invert_decorator |  | v
|  |  | node |  | v
|  |  | priority |  | v
|  |  | random |  | v
|  |  | sequence |  | v
|  | behaviour_tree |  |  | v
|  | init |  |  | v
|  | middleclass |  |  | v
|  | registry |  |  | v
| stl | list | core |  | v | v
|  |  | iterator |  | v | v
|  |  | node |  | v | v
|  | array |  |  | v | v
|  | queue |  |  | v | v
|  | stack |  |  | v | v
| class |  |  |  | v | v | v
| clolor |  |  |  | v | v | v
| comparator |  |  |  | v | v | v
| greatest_common_factor |  |  |  | v | v | v
| hexadecimal |  |  |  | v | v | v
| is_nil | [5 empty] | v
| jass_tool |  |  |  | v | v
| math_lib |  |  |  | v | v | v
| pairs_by_key |  |  |  | v | v | v
| point | [5 empty] | v
| random_number_generator |  |  |  | v | v | v
| table_copy |  |  |  | v | v
| table_merge |  |  |  | v | v
| task_tracker |  |  |  | v | v
| try_catch |  |  |  | v | v
war3 | api |  |  |  | v | v
| id |  |  |  | v | v
| order_id |  |  |  | v | v
main |  |  |  |  | v